## Sheet1
|  | Date: | 2017-09-26
|  | Defect Preparedby: | DANDA SATISH.
|  | Project: | Golars Environment PROJECT
S.No | DefectID | Defect Objective | Defect Precondition | DefectSteps | Expected Output | Actual Output | Priority | Seviority | Type | Status | Developer
1 | DF_GE_01 | Facilities Table Search is Not Work. | Login With USERID and PASSWORD | Managed Facilities Table Search Is Not Working | Search Table | Not Workiing | HIGH | HIGH | Functionality & UI | PENDING
2 | DF_GE_02 | FID in Facilities Table Some are Not working. | Login With USERID and PASSWORD | Managed Facilities Table Click on FID | Open Normally all list | Some are not Working | HIGH | HIGH | Functionality | PENDING
3 | DF_GE_03 | Add Attachemehnts in Problem . | Attach a new document in add attachment | Attach a new document in add attachment | Upload Successfully | 404 Error | HIGH | HIGH | Functionality | PENDING
after that return url is not Working
4 | DF_GE_04 | Attachements View UI Problem. | in Facility View Click On See TableGT & NF Attachements | Goto Facility View
|  |  |  | GT & NF Attachements Click On Attacemnts | UI Problem | Look & Feel Problem | HIGH | HIGH | Functionality | Pending
5 | DF_GE_05 | Scrool Problem in Facility View | in Facility View Click On See TableGT & NF Attachements | Goto Facility View
|  |  |  | GT & NF Attachements Click On Attacemnts | Table Scroll End After That Show Next Page | After Scroll page Not Moving | HIGH | HIGH | Functionality | PENDING
After Scrolling Table Content End it Will Show below Page
6 | DF_GE_06 | order Submit Last Page UI Problem | After Submit All Payment Methods Order Submit is Problem | Fill All The Payment Details Upto End | Look & Feel | Look & Feel Problem | HIGH | HIGH | Functionality | FIXED | SATISH
7 | DF_GE_07 | Payment History Table Records Problem In Payment | Goto Payments | Goto Payments List and See Payment History Table | Look & Feel and Functionality | Look & Feel Problem
|  | Table Alignment also Problem | See The Payment History Table It's Having Only 15 Records |  |  |  | HIGH | HIGH | Functionality & UI | PENDING
8 | DF_GE_08 | in ordersubmit page after refresh a page showing an error | in payment Submission order submit | in payment Submission order submit
|  |  | press F5 button it will Show an error | submit a payments press F5 | it will Redirect to Payment Page | Showing an Error | HIGH | HIGH | Functionality | PENDING
9 | DF_GE_09 | Company list table click one company URL in Table | Company List see the Table Of Companys | Goto Company List
|  |  | Click Link On Table | Click Any Company in Table | Open Company Information Normally | htmlentities() exp Problem | HIGH | HIGH | Functionality | Fixed
10 | DF_GE_10 | Payment History Table Confuse | Payments List See The Payments History
|  |  | Payment History Table Values Will Be Like FIFO | Goto Payments | Confuse list | FIFO List | HIGH | HIGH | Functionality | PENDING
See The Payment History
11 | DF_GE_11 | Payment Hisatory Table Created Date Is Wrong | Payments List See The Payments History | Goto Payments
|  |  |  | See The Payment History Created Date | Created Date Showing When Create a Payment | Created Date Problem | HIGH | HIGH | Functionality | PENDING
12 | DF_GE_12 | Payment Success Page UI Problem. On Mobile Devices | Goto Payments And Proceed Upto End | Goto Payments And Proceed Upto End | Look & Feel | Payment Success Page UI Problem. On Mobile Devices
|  |  | Payment Success Page UI Is Problem | Payment Success Page UI Is Problem |  |  | Medium | Medium | UI | PENDING
13 | DF_GE_13