## 3-7-2017
ACS Consultancy Software |  |  | BLACK - YELLOW - ORANGE - GREEN - SOLID GREEN/RED
Actiivities | Modules | Developer Assigned | Roles
MAIN PAGE - Front End | Main Page Front End | New Person ( Ravi) | Super Super Admin
Landing Page - Advertisement | HR + PMS | Ramesh (Ravi) | Super Admin
Exams/Questions | OPT Recruiter | Ashwin | Admin
Calender - Schedule | Bench Sales Recruiter | Ashwin | Sub Admin/Sr Manager
Team Calender | Trainer - Schedule/Calender | Ashwin | Manager
Cloud Based | Student/Consultant/Employee | Satish | Team Leader
3rd Party Consultant | Student Recruiter | Ashwin | Opt Recruiter
| Reports |  | Bench Sales
| Accounts | Ravi/Ashwin | Trainer
| College | Ramesh | Student/Emp/Consultant
| Consultancy - Multiple | Ramesh | Student Recruiter
| Vendor | Vamsi | Account Head
| Client | Satish | Account AR
| Guest House | Ramesh | Account AP
| Statistical Analytics |  | Accountant
| News Feed |  | Vendor
| Attorney | Shiva | Client
| Immigration | Shiva | Immigration
| Chat |  | HR
| Development Support |  | Third Party Login
| Hierarchy | Subrat | Sr Executive
| BDM | Subrat
| Third Part Consultancy | Athar
| Login Front End | New Person ( Ravi)
| Calender | Ashwin
| Admin | Ashwin
| Super Admin | Ashwin
| Super Super Admin | Ashwin
| Forum | Ravi
| ACS JOBS | Subrat
| SMS | Satish
| E-Mail | Satish
2017-07-12
Actiivities | New Modules Added (12-jul-2017)
| Bench Sales + Bench Sales Out Source |  | Bench Sale Out Source
Bench Sales Out Sourse
| Implementation | Vamshi
Work Report
| BDM | Subrat Start Working On BDM | Disscused About BDM | In Progress
| VENDOR | Vamshi Started. | Disscused About Vendor | In Progress
| HR | Ramesh Started. |  | In Progress
| Super Admin | Ashwin |  | In Progress
| Testing | Satish

## 13-7-2017
ACS Consultancy Software |  |  | BLACK - YELLOW - ORANGE - GREEN - SOLID GREEN/RED
Actiivities | Modules | Developer Assigned | Roles